## 30-60-90 Action Plan
Phase | Focus | Action | Success Measure | Status
First 30 Days | Learn the operation | Shadow each crew lead for a full shift | Written summary of every crew pain point | Done
First 30 Days | Learn the operation | Review the incident and complaint log from last season | Top five recurring issues identified | Done
First 30 Days | Stabilize the basics | Confirm fall program roster and instructor contracts | Zero unfilled classes at brochure deadline | Done
Days 31-60 | Quick wins | Move the field permit form online | Permit processing under 3 days | In Progress
Days 31-60 | Quick wins | Publish a weekly field closure alert email | Closures announced before 6 am | In Progress
Days 31-60 | Build the bench | Cross-train two staff on the pool chemistry system | Two certified backups on the schedule | Not Started
Days 61-90 | Plan the spring | Draft the spring program calendar with revenue targets | Draft approved by the director | Not Started
Days 61-90 | Plan the spring | Collect bids for the Birch Park surfacing job | Three comparable bids on file | Not Started
Days 61-90 | Report out | Present a 90 day summary to the city council | Summary delivered with next-quarter asks | Not Started