## Action Plan With Owners
Objective | Action | Owner | Support | Due | Status
Reopen the east pool by June | Drain, inspect, and repoint the pool shell | Teresa Whitaker | Doug Brennan | 2026-04-15 | Done
Reopen the east pool by June | Recertify lifeguard staff before opening day | Lila Fernandez | Aaron Pruitt | 2026-05-20 | Done
Reopen the east pool by June | Pass the county health inspection | Teresa Whitaker | Nina Kowalski | 2026-05-28 | Done
Grow fall program enrollment 15 percent | Publish the fall brochure online and in schools | Lila Fernandez | Nina Kowalski | 2026-08-15 | Done
Grow fall program enrollment 15 percent | Add evening pickleball leagues at the community center | Aaron Pruitt | Doug Brennan | 2026-09-12 | In Progress
Grow fall program enrollment 15 percent | Open scholarship slots for low income families | Teresa Whitaker | Lila Fernandez | 2026-09-26 | In Progress
Cut field maintenance overtime 20 percent | Rebid the mowing contract with set routes | Doug Brennan | Teresa Whitaker | 2026-10-10 | In Progress
Cut field maintenance overtime 20 percent | Move the in-house crew to weekday shifts | Doug Brennan | Aaron Pruitt | 2026-10-24 | Not Started
Replace playground surfacing at Birch Park | Order poured rubber surfacing before the freeze | Aaron Pruitt | Nina Kowalski | 2026-10-17 | Blocked
Replace playground surfacing at Birch Park | Schedule the install window with the vendor | Aaron Pruitt | Teresa Whitaker | 2026-11-07 | Not Started