## Corrective Action Plan
Issue | Root Cause | Action | Owner | Due | Verification
Warranty replies averaged 5 days in August | Claims routed to a shared mailbox nobody owned | Assign a named warranty queue owner each day | Harper Quinn | 2026-10-07 | Weekly mailbox audit against the owner roster
Refund requests stalled past the policy window | Approvals required a manager who worked weekends only | Raise the self-serve refund cap to 75 dollars | Devon Achebe | 2026-10-14 | Refund aging report stays under 48 hours for a month
Chat abandonment hit 40 percent early each week | Weekend backlog landed on a two-person shift | Add a float role from the training team for the first shift | Mia Sandoval | 2026-10-21 | Abandonment back under 15 percent for four straight weeks
Customers got conflicting setup advice | Three macro versions in circulation | Retire old macros and pin the current set | Mia Sandoval | 2026-10-28 | Macro report shows only current versions in use
Escalations bounced back half solved | Vague ticket summaries from the front line | Two-touch checklist before any escalation | Rajiv Menon | 2026-11-04 | Engineering return rate under 10 percent
Survey scores dipped after the firmware release | No proactive email about the known bug | Draft a proactive notice template for known issues | Zoe Callahan | 2026-11-11 | Notice sent within 24 hours of the next known-issue report
New agents took 6 weeks to reach quota | Training covered tools, not product | Add a product teardown day to onboarding | Harper Quinn | 2026-11-18 | Time-to-quota under 4 weeks for the next cohort
Social complaints sat unanswered overnight | No owner for the evening window | Fold social into the evening chat rotation | Devon Achebe | 2026-11-25 | No unanswered social post older than 12 hours
Duplicate tickets for the same order spiked | Order lookup tool timed out, so customers re-emailed | Fix the lookup index and add merge detection | Rajiv Menon | 2026-12-09 | Duplicate rate under 3 percent for two weeks
Callback promises were missed during the sale | Callback list lived in a personal notebook | Move callbacks to the shared queue with reminders | Zoe Callahan | 2026-12-16 | Zero missed callbacks in the weekly audit