## Simple Action Plan
Action | Owner | Due | Status | Outcome
Audit the last 200 tickets for reply-time outliers | Harper Quinn | 2026-10-02 | Done | 70 percent of slow replies came from one billing queue
Write macros for the ten most common questions | Mia Sandoval | 2026-10-09 | In Progress
Split the billing queue into its own inbox | Devon Achebe | 2026-10-16 | In Progress
Publish a first-reply-time dashboard for the team | Rajiv Menon | 2026-10-23 | Not Started
Train weekend coverage on the escalation matrix | Zoe Callahan | 2026-10-30 | Not Started
Set a two-touch rule before escalating to engineering | Harper Quinn | 2026-11-06 | Not Started
Rewrite the canned response for order status | Mia Sandoval | 2026-11-13 | Not Started
Review macro usage rates every Friday | Devon Achebe | 2026-11-20 | Not Started
Pilot a callback option for warranty claims | Zoe Callahan | 2026-12-04 | Blocked | Waiting on the telephony vendor sandbox
Cut the first-reply target from 24 hours to 8 | Rajiv Menon | 2026-12-18 | Not Started