## One-Page Business Case
Item | Summary | Owner | Approved
Problem | The single 320-ton press runs three shifts and still turns away about 15 percent of quoted work. | Renata Vasquez | TRUE
Proposal | Add a second press with dedicated tooling and one trained operator per shift. | Renata Vasquez | TRUE
Benefits | Added contribution margin of 800,000 dollars over three years and shorter quoted lead times. | Marcus Webb | TRUE
Costs | 523,000 dollars in capital plus 214,000 dollars in operator labor over three years. | Ingrid Lao | TRUE
Payback | Cumulative cash flow turns positive in month thirty under the expected case. | Ingrid Lao | TRUE
Risks | Softening demand in construction fasteners could stretch payback past four years. | Felix Grant | FALSE
Alternatives | Outsourcing overflow quotes a higher per-part cost and two extra weeks of lead time. | Renata Vasquez | FALSE
Decision | Approve a capital request of 523,000 dollars for the September board meeting. | Amelia Ortiz | FALSE