## Standard Business Case
Section | Content | Owner | Status
Problem | The downtown branch lobby serves 1,900 customers a week through three teller windows built for half that volume, and midday waits now average fourteen minutes. | Diane Ackerman | Approved
Problem | The branch is losing an estimated 6 percent of walk-in checking accounts each quarter to a newer competitor two blocks away. | Marcus Bell | Approved
Options | Renovate the existing 2,400 square foot branch with four self-serve kiosks and two advisory offices. | Diane Ackerman | Approved
Options | Lease a ground-floor suite in the new market hall and relocate the branch within eighteen months. | Priya Shah | In Review
Options | Close the branch and push customers to digital channels with a video-teller lobby. | Marcus Bell | In Review
Recommendation | Renovate in place: it keeps the charter location, costs roughly 40 percent less than relocation, and lands before the holiday deposit season. | Diane Ackerman | Approved
Benefits | Midday wait time falls below five minutes, supporting a three point lift in new checking accounts. | Tom Evers | Approved
Benefits | Two advisory offices let the wealth team see 25 more households a month. | Sofia Marin | Approved
Costs | Construction, fixtures, and kiosks come to 610,000 dollars in capital, phased over two quarters. | Walter Chen | Approved
Costs | A two-week temporary closure routes service to the Elm Street branch during the lobby rebuild. | Walter Chen | In Review
Risks | Construction overruns in the historic district; contingency held at 12 percent of construction cost. | Dana Whitfield | In Review
Risks | Kiosk adoption runs below plan if staffing hours and floor coaching stay unchanged. | Sofia Marin | Draft