## Campaign Launch Tracker
Task | Channel | Asset | Owner | Due Date | Days Out | Flag | Status
Segment the list for launch sends | Email | Segments: VIP, engaged, lapsed | Meg Liu | 2026-08-21 | 0 |  | Done
Draft the launch announcement email | Email | Announcement email | Meg Liu | 2026-08-28 | 2 | On track | In Progress
VIP early-access email | Email | Early-access send to VIP segment | Meg Liu | 2026-09-03 | 8 | On track | Not Started
Schedule the launch-day send | Email | Launch email, scheduled 8 am | Meg Liu | 2026-09-09 | 14 | On track | Not Started
Build the post-launch nurture flow | Email | 3-email nurture sequence | Meg Liu | 2026-09-15 | 20 | On track | Not Started
Ship influencer seeding kits | Social | 24 seeding kits | Jess Moran | 2026-08-22 | 0 |  | Done
Write and schedule teaser posts | Social | 9 teaser posts | Jess Moran | 2026-08-26 | 0 | Overdue | In Progress
Assemble the launch-day post pack | Social | Feed post, story set, reel | Jess Moran | 2026-09-08 | 13 | On track | Not Started
Partner reels go live | Social | 6 partner reels | Jess Moran | 2026-09-10 | 15 | On track | Not Started
Set the launch-week reply rota | Social | Community reply rota | Jess Moran | 2026-09-09 | 14 | On track | Not Started
Brief design on paid concepts | Paid | Brief: 3 concepts | Tariq Aziz | 2026-08-14 | 0 |  | Done
Deliver ad creative in all sizes | Paid | 12 assets, 3 sizes | Cole Bennett | 2026-08-25 | 0 | Overdue | Blocked
Approve the budget flighting plan | Paid | Flighting plan | Tariq Aziz | 2026-08-29 | 3 | On track | In Progress
Build prospecting and retargeting campaigns | Paid | 2 campaigns, 6 ad sets | Tariq Aziz | 2026-09-04 | 9 | On track | Not Started
QA pixels and UTM tags | Paid | UTM sheet + pixel check | Tariq Aziz | 2026-09-05 | 10 | On track | Not Started
Retouch product photography | Content | 42 final images | Cole Bennett | 2026-08-20 | 0 |  | Done
Final cut of the hero video | Content | 60-second hero video | Cole Bennett | 2026-08-27 | 1 | On track | In Progress
Draft the launch blog post | Content | Hero blog post | Meg Liu | 2026-09-01 | 6 | On track | In Progress
Write FAQ copy for support | Content | FAQ one-pager | Meg Liu | 2026-09-05 | 10 | On track | Not Started
Finalize the press release | PR | Press release | April Chen | 2026-08-25 | 0 |  | Done
Mail samples to press list | PR | 15 press samples | April Chen | 2026-08-21 | 0 |  | Done
Pitch the media list | PR | Pitches to 40 outlets | April Chen | 2026-08-29 | 3 | On track | In Progress
Embargo lifts | PR | Embargo: 8 am launch day | April Chen | 2026-09-10 | 15 | On track | Not Started
Build the launch landing page | Web | Launch landing page | Drew Santos | 2026-09-02 | 7 | On track | In Progress
Load product pages, keep hidden | Web | 6 product pages | Drew Santos | 2026-09-05 | 10 | On track | Not Started
QA mobile and test checkout | Web | Pre-launch QA checklist | Drew Santos | 2026-09-08 | 13 | On track | Not Started
Swap the homepage hero | Web | Homepage takeover | Drew Santos | 2026-09-10 | 15 | On track | Not Started
Lock pop-up logistics for launch week | Event | Pop-up runsheet | Jess Moran | 2026-09-06 | 11 | On track | Not Started