## Launch Day Run of Show
Time | Moment | Channel | Owner | Depends On | Status
6:30 am | Final site check on staging | Web | Drew Santos |  | Live
7:00 am | Product pages flipped to visible | Web | Drew Santos | Site check | Live
7:15 am | Homepage hero swapped | Web | Drew Santos | Product pages live | Live
7:30 am | Test order placed and refunded | Web | Jess Moran | Homepage live | Live
8:00 am | Press embargo lifts | PR | April Chen | Site live | Live
8:00 am | Launch email sends | Email | Meg Liu | Site live | Live
8:15 am | Founder post goes up | Social | Jess Moran | Embargo lifted | Scheduled
8:30 am | Feed post and story set publish | Social | Jess Moran | Founder post | Scheduled
9:00 am | Paid campaigns switched on | Paid | Tariq Aziz | Pixel check green | Scheduled
9:30 am | Partner reels start going live | Social | Jess Moran |  | Scheduled
10:00 am | First metrics checkpoint | Content | Jess Moran | Email + social live | Scheduled
11:00 am | Reply rota takes over comments | Social | Meg Liu |  | Scheduled
12:30 pm | Midday war-room check-in | Event | Jess Moran | Metrics checkpoint | Scheduled
2:00 pm | Press coverage roundup shared | PR | April Chen |  | Scheduled
4:00 pm | Retargeting audience seeded | Paid | Tariq Aziz | Paid live 6 hours | Scheduled
6:00 pm | Day-one wrap numbers posted | Content | Jess Moran |  | Scheduled