## Homeowner Sign-Off Sheet
Change | Price ($) | Days Added | Homeowner | How Approved | Decision | Sign-Off Date
Frameless glass shower door upgrade | 1450 | 2 | Erin Naylor | Signed on site | Approved | 2026-06-03
Heated tile floor, mat and thermostat | 980 | 1 | Erin Naylor | Email | Approved | 2026-06-05
Move washer box to the hall closet | 1720 | 2 | Drew Naylor | Signed on site | Approved | 2026-06-10
Upgrade vanity to a double sink | 1240 | 1 | Erin Naylor | Text message | Approved | 2026-06-14
Tile wainscot in the water closet | 640 | 1 | Drew Naylor | Verbal, needs follow-up | Waiting
Replace brittle supply lines found at demo | 210 | 0 | Erin Naylor | Text message | Approved | 2026-06-17
Pocket door instead of the swing door | 830 | 1 | Drew Naylor | Email | Waiting
Recessed niche at the tub wall | 380 | 0 | Erin Naylor | Signed on site | Approved | 2026-06-20
Skylight over the shower | 2600 | 3 | Drew Naylor | Email | Declined | 2026-06-22
Towel warmer circuit and install | 540 | 0 | Erin Naylor | Verbal, needs follow-up | Waiting
6 approved, 3 awaiting sign-off | 5980 | 6