## Job Change Order Log
CO # | Change Requested | Asked By | Date | Price ($) | Days Added | Status | Billed
CO-01 | Add under-cabinet lighting, 4 runs | Homeowner | 2026-05-12 | 680 | 1 | Approved | TRUE
CO-02 | Move fridge water line for the new island | Homeowner | 2026-05-14 | 450 | 1 | Approved | TRUE
CO-03 | Rot repair at sink wall, found during demo | Field | 2026-05-16 | 1240 | 2 | Approved | TRUE
CO-04 | Upgrade to stone sill at the bay window | Homeowner | 2026-05-21 | 390 | 0 | Declined | FALSE
CO-05 | Switch to soft-close hinges, all cabinets | Homeowner | 2026-05-27 | 520 | 0 | Approved | FALSE
CO-06 | Add outlet and USB at the coffee bar | Homeowner | 2026-06-02 | 260 | 0 | Approved | TRUE
CO-07 | Re-route heat duct hit by island footing | Field | 2026-06-05 | 880 | 1 | Approved | FALSE
CO-08 | Paint the dining room ceiling too | Homeowner | 2026-06-10 | 340 | 1 | Pending | FALSE
CO-09 | Pot filler at the range | Homeowner | 2026-06-12 | 610 | 0 | Pending | FALSE
CO-10 | Replace brittle shutoff valves under sink | Field | 2026-06-16 | 180 | 0 | Approved | FALSE
CO-11 | Tile backsplash to the ceiling behind range | Homeowner | 2026-06-20 | 720 | 1 | Pending | FALSE
CO-12 | Haul old cabinets to the donation center | Homeowner | 2026-06-24 | 150 | 0 | Pending | FALSE
Approved so far | 7 of 12 approved, 4 still pending |  |  | 4210 | 5