## Multi-Job Change Order Tracker
Job | Change | Date | Price ($) | Days Added | Status
Delgado Kitchen | Under-cabinet lighting | 2026-05-12 | 680 | 1 | Approved
Delgado Kitchen | Rot repair at sink wall | 2026-05-16 | 1240 | 2 | Approved
Pruitt Deck | Upgrade to composite decking | 2026-05-20 | 2150 | 0 | Approved
Pruitt Deck | Privacy screen at the north rail | 2026-05-28 | 760 | 1 | Pending
Ash Street Rental | Replace double-tapped sub-panel | 2026-06-01 | 1380 | 1 | Approved
Naylor Bath | Glass shower door upgrade | 2026-06-03 | 1450 | 2 | Approved
Naylor Bath | Heated tile floor | 2026-06-05 | 980 | 1 | Approved
Delgado Kitchen | Pot filler at the range | 2026-06-12 | 610 | 0 | Pending
Pruitt Deck | Wrap posts in cedar | 2026-06-14 | 540 | 1 | Declined
Ash Street Rental | Paint both bedrooms while vacant | 2026-06-16 | 880 | 2 | Approved
Naylor Bath | Pocket door swap | 2026-06-18 | 830 | 1 | Pending
Delgado Kitchen | Backsplash to the ceiling | 2026-06-20 | 720 | 1 | Pending
Pruitt Deck | Solar cap lights on the posts | 2026-06-24 | 320 | 0 | Approved
Ash Street Rental | New exterior door hardware | 2026-06-26 | 240 | 0 | Pending
| Approved across all jobs |  | 9080 | 9
| 5 asks still waiting on an answer |  | 3160