## Bank Draw Request Tracker
Draw # | Date Submitted | Work Covered | Requested ($) | Inspection Date | Status | Funded Date
Draw 1 | 2026-03-16 | Lot clearing, foundation, slab | 58200 | 2026-03-20 | Funded | 2026-03-27
Draw 2 | 2026-04-14 | Framing labor and lumber package | 96400 | 2026-04-17 | Funded | 2026-04-24
Draw 3 | 2026-05-11 | Roofing, windows, exterior doors | 64800 | 2026-05-14 | Funded | 2026-05-21
Draw 4 | 2026-06-08 | Rough mechanicals, all three trades | 71500 | 2026-06-11 | Funded | 2026-06-19
Draw 5 | 2026-07-06 | Insulation and drywall | 43200 | 2026-07-09 | Inspection Scheduled
Draw 6 |  | Cabinets, trim, interior paint | 47600 |  | Upcoming
Draw 7 |  | Flooring, fixtures, appliances | 39400 |  | Upcoming
Final |  | Punch list and certificate of occupancy | 40900 |  | Upcoming
Funded to date |  |  | 290900
Left on the loan |  |  | 171100