## Remodel Payment Schedule
Payment | Due When | Amount ($) | % of Total | Status | Paid Date
Deposit | At contract signing | 4850 | 10 | Paid | 2026-05-04
Payment 2 | Demo done, cabinets ordered | 9700 | 20 | Paid | 2026-05-18
Payment 3 | Rough plumbing and electrical passed | 9700 | 20 | Paid | 2026-06-08
Payment 4 | Drywall closed, paint complete | 9700 | 20 | Due Now
Payment 5 | Cabinets and counters installed | 9700 | 20 | Upcoming
Final | Punch list complete, final walkthrough | 4850 | 10 | Upcoming
Collected so far |  | 24250 | 50
Left to collect |  | 24250