## Residential Draw Schedule
Draw | Payment Trigger | % of Contract | Amount ($) | Status | Paid Date
Deposit | Contract signed, permits filed | 10 | 18600 | Paid | 2026-04-06
Draw 1 | Foundation poured and backfilled | 15 | 27900 | Paid | 2026-04-28
Draw 2 | Framing complete, sheathing inspected | 20 | 37200 | Paid | 2026-05-22
Draw 3 | Roof dried in, windows and doors set | 15 | 27900 | Paid | 2026-06-12
Draw 4 | Rough plumbing, electrical, HVAC passed | 15 | 27900 | Invoiced
Draw 5 | Drywall hung and finished | 10 | 18600 | Upcoming
Draw 6 | Cabinets, trim, and flooring complete | 10 | 18600 | Upcoming
Final | Punch list done, final inspection passed | 5 | 9300 | Upcoming
Paid to date | 60 percent of the contract collected |  | 111600
Left to collect |  |  | 74400