## Standard Creative Brief
Section | Prompt | Answer | Status
Objective | What must this work achieve? | Launch the fall 2026 line with a campaign that positions Trailmark as the durable choice for wet-climate hikers | Approved
Audience | Who are we talking to? | Weekend backpackers in the Pacific Northwest, ages 28 to 45, replacing gear every two to three years | Approved
Key Message | The single thing to remember | Trailmark shells are built for the forecast you actually get, not the one you hoped for | In Review
Mandatories | What must appear | Logo on every asset, the recycled-fabric claim wording, trailmark.example URL, legal line on packaging renders | Approved
Tone | How it should feel | Plainspoken, weathered, confident; short sentences, real trail names, no hype words | In Review
Deliverables | What we need back | Three hero images, one 30 second cut, six social crops, landing page header, email banner | Draft
Timeline | Key milestones | Concepts 2026-10-09, first round 2026-10-23, final files 2026-11-06, live 2026-11-16 | Draft
Budget | What we can spend | 48,000 production cap, 12,000 media test, agency hours capped at 220 | In Review
Approvals | Who signs off | Brand director Marisol Vega, then legal review by Dana Whitfield before any public asset | Approved
Success Metric | How we judge it | Landing page conversion above 3.5 percent and 800 email signups in the first month | Draft