## Gantt With Dependencies
Task | Owner | Start | End | Depends On | Status
Scope lock | Petra Lindell | 2026-09-21 | 2026-09-25 | None | Done
UI freeze | Oscar Nygaard | 2026-10-02 | 2026-10-09 | Scope lock | Done
Core feature build | Bea Fontaine | 2026-09-28 | 2026-10-23 | Scope lock | In Progress
App store assets | Camille Roy | 2026-10-12 | 2026-10-23 | UI freeze | In Progress
Localization | Marcus Webb | 2026-10-19 | 2026-11-06 | UI freeze | In Progress
Beta build | Oscar Nygaard | 2026-10-26 | 2026-11-06 | Core feature build | Not Started
Beta feedback fixes | Felix Marsh | 2026-11-09 | 2026-11-13 | Beta build | Not Started
Regression pass | Nadia Petrova | 2026-11-09 | 2026-11-20 | Beta build | Not Started
Release notes | Lena Torres | 2026-11-16 | 2026-11-24 | Beta feedback fixes | Not Started
Store submission | Tomas Rivera | 2026-11-23 | 2026-11-25 | App store assets | Not Started
Support macros | Rafael Cisneros | 2026-11-23 | 2026-12-02 | Release notes | Not Started
Launch | Petra Lindell | 2026-12-03 | 2026-12-03 | Store submission | Not Started