## Gantt With Milestones
Type | Name | Date | Owner | Done
Milestone | Lease signed | 2026-08-14 | Otis Brandt | TRUE
Task | Demolition complete | 2026-09-25 | Hank Whitfield | TRUE
Milestone | Framing inspection passed | 2026-10-09 | Devi Anand | FALSE
Task | Electrical rough-in complete | 2026-10-16 | Marcus Webb | FALSE
Milestone | Drywall inspection passed | 2026-10-23 | Camille Roy | FALSE
Task | Flooring complete | 2026-11-10 | Bea Fontaine | FALSE
Task | Millwork installed | 2026-11-25 | Nadia Petrova | FALSE
Milestone | Furniture delivered | 2026-12-04 | Tomas Rivera | FALSE
Task | IT setup complete | 2026-12-11 | Lena Torres | FALSE
Milestone | Punch list closed | 2026-12-18 | Otis Brandt | FALSE
Milestone | Staff move-in day | 2026-12-21 | June Hartley | FALSE
Milestone | Open house for clients | 2027-01-08 | June Hartley | FALSE