## Simple Gantt
Task | Owner | Start | End | Duration (days) | Percent Complete
Demolition and strip-out | Hank Whitfield | 2026-09-14 | 2026-09-25 | 10 | 100
Framing and drywall | Devi Anand | 2026-09-28 | 2026-10-09 | 10 | 70
Electrical rough-in | Marcus Webb | 2026-10-05 | 2026-10-16 | 10 | 30
Data and network cabling | Rafael Cisneros | 2026-10-12 | 2026-10-21 | 8 | 10
Ceiling grid and lighting | Camille Roy | 2026-10-19 | 2026-10-30 | 10 | 0
Flooring | Bea Fontaine | 2026-11-02 | 2026-11-10 | 7 | 0
Painting | Felix Marsh | 2026-11-05 | 2026-11-13 | 7 | 0
Millwork and reception desk | Nadia Petrova | 2026-11-09 | 2026-11-25 | 12 | 0
Furniture delivery and install | Tomas Rivera | 2026-11-30 | 2026-12-04 | 5 | 0
IT equipment setup | Lena Torres | 2026-12-07 | 2026-12-11 | 5 | 0
Punch list and walkthrough | Otis Brandt | 2026-12-14 | 2026-12-18 | 5 | 0