## OKR-Aligned Roadmap
Objective | Key Result | Initiative | Quarter | Owner | Progress (%) | Health
Land the enterprise segment | 5 signed contracts over 100 seats | SSO with Okta and Azure AD | Q4 2026 | Maya Okafor | 55 | At risk
Land the enterprise segment | Pass 10 security reviews first try | Audit log export | Q4 2026 | Kat Weber | 30 | Behind
Land the enterprise segment | Median rollout under 14 days | Onboarding checklist v2 | Q4 2026 | Rui Costa | 72 | On track
Make reports the weekly habit | 60% of accounts open a report weekly | Scheduled report emails | Q4 2026 | Lena Ivanov | 80 | On track
Make reports the weekly habit | Guest links used by 500 accounts | Read-only guest links | Q4 2026 | Maya Okafor | 45 | At risk
Make reports the weekly habit | Alert-to-action under one day | Slack threshold alerts | Q1 2027 | Lena Ivanov | 15 | Behind
Cut churn below 2% monthly | Save 40% of at-risk renewals | Churn-signal triage rota | Q4 2026 | Priya Shah | 62 | At risk
Cut churn below 2% monthly | API-limit complaints to zero | Higher API rate limits | Q4 2026 | Kat Weber | 85 | On track
Cut churn below 2% monthly | Close the loop on 90% of requests | In-product changelog | Q4 2026 | Maya Okafor | 76 | On track
Open the data-team wedge | 3 design partners live on sync | Warehouse-native sync | Q1 2027 | Lena Ivanov | 10 | Behind
Open the data-team wedge | Forecast beta with 20 accounts | Forecasting on any metric | Q1 2027 | Maya Okafor | 5 | Behind
Open the data-team wedge | Usage analytics on every report | Report usage analytics | Q1 2027 | Rui Costa | 20 | Behind