## Quarterly Product Roadmap
Initiative | Quarter | Team | Objective | Effort (Weeks) | Status
SSO with Okta and Azure AD | Q4 2026 | Platform | Unblock enterprise rollouts | 6 | Build
Scheduled report emails | Q4 2026 | Core app | Cut manual reporting to zero | 3 | Build
Onboarding checklist v2 | Q4 2026 | Core app | Raise trial-to-paid conversion | 4 | Design
Higher API rate limits | Q4 2026 | Platform | Keep integration-heavy accounts | 2 | Build
Read-only guest links | Q4 2026 | Core app | Make reports the shared artifact | 3 | Design
Audit log export | Q1 2027 | Platform | Pass enterprise security reviews | 3 | Discovery
Slack threshold alerts | Q1 2027 | Data | Surface metric drops same-day | 4 | Discovery
Custom fields on accounts | Q1 2027 | Core app | Model customer business natively | 6 | Discovery
Report usage analytics | Q1 2027 | Data | Show which reports earn their keep | 3 | Discovery
Mobile widgets | Q1 2027 | Mobile | Put one number on the home screen | 5 | Discovery
Warehouse-native sync | Q2 2027 | Data | Read the customer warehouse directly | 8 | Discovery
Forecasting on any metric | Q2 2027 | Data | Keep trend modeling in-product | 6 | Discovery
Workspace consolidation tools | Q2 2027 | Core app | Clean up grown accounts | 4 | Discovery
Dark theme | Q2 2027 | Mobile | Answer the top community request | 3 | Discovery
In-product changelog | Q4 2026 | Core app | Close the loop with requesters | 2 | Shipped
EU data residency | Q2 2027 | Platform | Open EU enterprise pipeline | 8 | Discovery