## Project Planner With Timeline
Phase | Task | Start | End | Owner
Permits | Submit permit drawings to city | 2026-02-02 | 2026-02-13 | Ray Delgado
Permits | Receive permit approval | 2026-02-16 | 2026-03-06 | Chuck Brennan
Site Prep | Mobilize and set site fencing | 2026-03-09 | 2026-03-13 | Ana Petrova
Site Prep | Demolish existing interior | 2026-03-16 | 2026-03-27 | Marcus Hale
Rough-In | Electrical and data rough-in | 2026-03-30 | 2026-04-17 | Ray Delgado
Rough-In | Plumbing and HVAC rough-in | 2026-04-06 | 2026-04-24 | Tessa Roy
Rough-In | Rough inspection signoff | 2026-04-27 | 2026-04-29 | Chuck Brennan
Finishes | Drywall, paint, and flooring | 2026-05-04 | 2026-05-29 | Ana Petrova
Finishes | Furniture and workstation install | 2026-06-01 | 2026-06-12 | Doug Farrow
Closeout | Punch list and final walkthrough | 2026-06-15 | 2026-06-19 | Chuck Brennan