## Simple Project Planner
Task | Owner | Due | Status | Notes
Confirm gala venue contract | Marisol Vance | 2026-03-06 | Done | Signed and countersigned copy filed
Book catering tasting | Theo Aldrich | 2026-03-20 | Done | Two finalists selected
Send save-the-date to donor list | Dana Whitfield | 2026-04-03 | In Progress | List split into two segments
Reserve auction items | Priya Nair | 2026-04-17 | In Progress | Twelve of twenty items pledged
Finalize AV quote | Sam Okafor | 2026-05-01 | Not Started | Waiting on vendor revisions
Recruit volunteer captains | Lena Brooks | 2026-05-08 | Not Started | Goal of six captains
Print invitation suite | Marisol Vance | 2026-05-15 | Not Started | Needs final copy approval
Brief board on sponsorship totals | Dana Whitfield | 2026-04-10 | Blocked | Two pledges still unsigned
Set up online ticket sales | Theo Aldrich | 2026-04-24 | In Progress | Test orders placed
Walkthrough with venue ops lead | Marisol Vance | 2026-06-05 | Not Started | Room layout due same week