## Software Release Checklist
Item | Owner | Due | Blocks Release | Status
Code freeze |  | 2026-09-04 |  | In Progress
Feature branches merged to main | Lena Ivanov | 2026-09-02 | TRUE | In Progress
Feature flags default states set | Kat Weber | 2026-09-03 | TRUE | In Progress
Release notes drafted | Maya Okafor | 2026-09-03 | FALSE | In Progress
Migration scripts reviewed | Lena Ivanov | 2026-09-04 | TRUE | Not Started
Version bumped and changelog cut | Kat Weber | 2026-09-04 | FALSE | Not Started
QA and staging |  | 2026-09-09 |  | Not Started
Full regression suite green on staging | Owen Diaz | 2026-09-07 | TRUE | Not Started
Migration rehearsed on a prod-size copy | Lena Ivanov | 2026-09-08 | TRUE | Not Started
Load test at 2x normal traffic | Owen Diaz | 2026-09-08 | FALSE | Not Started
Accessibility pass on changed screens | Rui Costa | 2026-09-08 | FALSE | Not Started
Rollback procedure walked through | Kat Weber | 2026-09-09 | TRUE | Not Started
Support briefed on changes and known issues | Priya Shah | 2026-09-09 | FALSE | Not Started
Launch day |  | 2026-09-10 |  | Not Started
Deploy to production, canary first | Lena Ivanov | 2026-09-10 | TRUE | Not Started
Smoke test the critical paths | Owen Diaz | 2026-09-10 | TRUE | Not Started
Error rates and latency watched for 2 hours | Kat Weber | 2026-09-10 | TRUE | Not Started
Feature flags flipped for all accounts | Lena Ivanov | 2026-09-10 | TRUE | Not Started
Release notes published | Maya Okafor | 2026-09-10 | FALSE | Not Started
In-app announcement live | Rui Costa | 2026-09-10 | FALSE | Not Started
Post-release |  | 2026-09-17 |  | Not Started
Day-one metrics reviewed against baseline | Maya Okafor | 2026-09-11 | FALSE | Not Started
Support tickets tagged to the release triaged | Priya Shah | 2026-09-12 | FALSE | Not Started
Requesters notified their feature shipped | Maya Okafor | 2026-09-12 | FALSE | Not Started
Retro held and actions filed | Lena Ivanov | 2026-09-16 | FALSE | Not Started
Stale feature flags removed | Kat Weber | 2026-09-17 | FALSE | Not Started