## Project Risk Assessment
Risk | Category | Probability | Impact | Score | Response | Owner
Legacy shipment data fails the import validation rules | Technical | 3 | 5 | 15 | Mitigate | Priya Nair
Carrier integrations slip past the cutover weekend | Vendor | 3 | 4 | 12 | Mitigate | Tom Redmond
Warehouse staff resist the new scanning workflow | People | 4 | 3 | 12 | Mitigate | Alicia Fontaine
Migration runbooks underestimate downtime by half a day | Schedule | 2 | 4 | 8 | Mitigate | David Kessler
Parallel running doubles hosting spend for a quarter | Budget | 3 | 2 | 6 | Accept | Nadia Osei
Scope grows to include the customer portal rewrite | Scope | 2 | 5 | 10 | Avoid | Priya Nair
Data residency rules block hosting in the chosen region | Technical | 1 | 5 | 5 | Transfer | David Kessler
Key migration engineer leaves mid-project | People | 2 | 4 | 8 | Mitigate | Tom Redmond
Test environment quota limits the full-volume rehearsal | Technical | 3 | 3 | 9 | Mitigate | Priya Nair
Carrier EDI specification changes during the migration window | Vendor | 1 | 4 | 4 | Accept | Nadia Osei