## Marketing Campaign Timeline
Asset | Channel | Draft Date | Publish Date | Owner | Status
Exhibition teaser video | Social | 2026-11-09 | 2026-12-07 | Greta Salomon | Done
Member preview invitation | Email | 2026-12-14 | 2027-01-08 | Lena Torres | Draft
Press kit | Press | 2026-12-04 | 2027-01-05 | Cyrus Hale | In Review
Email announcement to members | Email | 2026-12-11 | 2027-01-12 | Lena Torres | Draft
School program flyer | Print | 2026-12-18 | 2027-01-19 | Greta Salomon | Draft
Sponsor acknowledgment ad | Print | 2027-01-11 | 2027-02-01 | Camille Roy | In Review
Countdown social series | Social | 2027-01-18 | 2027-02-05 | Greta Salomon | Not Started
Opening weekend flyer | Print | 2027-01-08 | 2027-01-29 | Camille Roy | Not Started
Local radio spot | Paid | 2027-01-25 | 2027-02-08 | Cyrus Hale | Not Started
Opening night remarks | Events | 2027-02-05 | 2027-02-09 | June Hartley | Not Started