## Product Launch Timeline
Workstream | Task | Start | End | Depends On | Owner
Engineering | Scope lock | 2026-09-28 | 2026-10-02 | None | Petra Lindell
Engineering | Feature freeze | 2026-10-05 | 2026-10-30 | Scope lock | Oscar Nygaard
Engineering | Release candidate 1 | 2026-11-02 | 2026-11-13 | Feature freeze | Oscar Nygaard
Quality | Regression testing | 2026-11-09 | 2026-11-27 | Release candidate 1 | Bea Fontaine
Quality | Penetration test | 2026-11-16 | 2026-11-27 | Release candidate 1 | Felix Marsh
Compliance | SOC 2 evidence collection | 2026-10-12 | 2026-11-20 | Scope lock | Nadia Petrova
Marketing | Positioning and messaging | 2026-10-19 | 2026-11-06 | Scope lock | Cyrus Hale
Marketing | Launch page and demo video | 2026-11-09 | 2026-12-04 | Positioning and messaging | Lena Torres
Sales | Battlecards and pricing sheet | 2026-11-16 | 2026-12-04 | Positioning and messaging | Marcus Webb
Support | Help center updates | 2026-11-23 | 2026-12-04 | Release candidate 1 | Tomas Rivera
Support | Support macro refresh | 2026-11-30 | 2026-12-08 | Help center updates | Tomas Rivera
Launch | Launch day | 2026-12-08 | 2026-12-08 | Support macro refresh | Petra Lindell