## Project Timeline
Phase | Milestone | Start | End | Owner | Status
Concept Design | Exhibit storyline approved | 2026-08-03 | 2026-09-04 | June Hartley | Done
Concept Design | Gallery layout signed off | 2026-09-07 | 2026-09-25 | Rafael Cisneros | Done
Schematic Design | Case and mount specs approved | 2026-09-28 | 2026-10-16 | Camille Roy | In Progress
Schematic Design | Lighting plan approved | 2026-10-05 | 2026-10-23 | Otis Brandt | In Progress
Fabrication | Artifact mounts fabricated | 2026-11-02 | 2026-12-18 | Devi Anand | Not Started
Fabrication | Interactive kiosks built | 2026-11-09 | 2027-01-08 | Marcus Webb | At Risk
Gallery Preparation | Gallery walls repainted | 2026-12-21 | 2027-01-08 | Hank Whitfield | Not Started
Education | School program materials ready | 2026-12-14 | 2027-01-15 | Greta Salomon | Not Started
Installation | Cases installed | 2027-01-11 | 2027-01-22 | Devi Anand | Not Started
Installation | Artifacts placed and lit | 2027-01-25 | 2027-02-05 | June Hartley | Not Started
Opening Week | Press preview event | 2027-02-09 | 2027-02-09 | Cyrus Hale | Not Started
Opening Week | Public opening day | 2027-02-12 | 2027-02-12 | June Hartley | Not Started