## Construction Work Order
Task | Location | Crew | Start | End | Hours | Materials
Frame interior partition, Suite 210 | Building B, second floor | Tom Okonkwo | 2026-10-01 | 2026-10-03 | 24 | Steel studs, track, drywall
Rough-in plumbing for break room | Building B, second floor | Priya Raghavan | 2026-10-02 | 2026-10-06 | 30 | PEX, fittings, shutoff valves
Pour walkway at dock apron | North dock | Sam Delgado | 2026-10-05 | 2026-10-06 | 16 | Concrete, rebar mesh, curing compound
Install exhaust fan, commissary | Building C, kitchen | Nadia Brooks | 2026-10-07 | 2026-10-08 | 12 | Fan unit, duct sections, hardware
Paint corridors, floor two | Building B | Renee Calloway | 2026-10-08 | 2026-10-10 | 20 | Primer, paint, rollers, tape
Set new parking signage | North lot | Bo Lindqvist | 2026-10-09 | 2026-10-09 | 6 | Signs, posts, concrete mix
Replace dock door seals | South dock | Dario Fuentes | 2026-10-13 | 2026-10-14 | 10 | Seal kits, fasteners
Final clean and punch walk | Building B, second floor | Marta Ellison | 2026-10-15 | 2026-10-15 | 8 | Cleaning supplies